## Plan
Project Plan & Gantt Chart
Set the project start date in C3 (a Monday). Fill tasks, start week and length — the bars draw themselves.
Project start:
# | Task | Owner | Start week | Weeks | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
1 | Requirements & proposal |  | 1 | 2 | Not started
2 | System design (ER, architecture, UI) |  | 2 | 2 | Not started
3 | Backend API |  | 3 | 4 | Not started
4 | Frontend |  | 4 | 4 | Not started
5 | Integration & AI features |  | 6 | 3 | Not started
6 | Testing |  | 8 | 3 | Not started
7 | Deployment |  | 10 | 1 | Not started
8 | Final report |  | 9 | 4 | Not started
9 | Presentation & viva prep |  | 12 | 2 | Not started
10
11
12
13
14
15
16
17
18
19
20